## Sheet1
R&D
1 | AWS Alexa R&D | Done | 2018-05-01
2 | Alexa sample implementation | Done | 2018-05-01
3 | ASP.NET Core Web API help pages with Swagger / Open API [Swashbuckle/Nswag = I used Nswag] |  | 2018-05-13
4 | Sound input - xamarin form
5 | set reminder - xamarin form
6 | share list - xamarin form
Mobile applicatoion and cloud integration
1 | Project Infrastructure creation | Done | 2018-05-06
2 | Github source control integration | Done | 2018-05-06
Dispplay Grocery List in App
1 | Azure db creation - powershell scripts
2 | Modify service to get data from Azure | In Progress | 2018-05-06
3 | Simple dummy list display
4 | Actual List display
5 | Apply font
6 | Improve UI for list display
Insert Grocery entry in app
4 | Add category
5 | Add grocery in list
6 | database creation
7 | Types creation
8 | db connectivity
9 | add/edit list with actual database
10 | proper font on UI
11 | show menu hambrurger on screen
12 | show plus icon to add new item
13 | set reminder for grocery list
14 | share grocery list with others
15 | Offline sync | OnHold
16 | Connection with azure
Devops activities
Documentation
1 | Create general structure diagram | Done

## info
2018-04-14
1 | AWS toolkit for visual studio is downloaded :- | https://aws.amazon.com/visualstudio/
2 | Alexa skill tutorial referred from here | http://matthiasshapiro.com/2017/02/10/tutorial-alexa-skills-in-c-setup/
3 | Alexa skill referance link to refer | http://timheuer.com/blog/archive/2016/12/12/amazon-alexa-skill-using-c-sharp-dotnet-core.aspx

## Sheet2
grocerymanagemntcosmosdb ->grocerymanagemnt-database -> grocerymanagemnt-collection
Database structure
Grocery
Id
Name
| Quantity | { "id": "1", "category": "Grocery", "name": "wheat", "description": "for roti", "quantity":"1","specification":"kg","isComplete": false }
| Specification | { "id": "2", "category": "Grocery", "name": "jaggery", "description": "brown color soft jaggery", "quantity":"1","specification":"kg","isComplete": false }
IsComplete